## Sheet1
Tasks | WEEKS
| June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
App implementation | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Web Framework engineering | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra | Web Fra
Public pages / interactions | Public pa | Public pa | Public pa | Public pa | Public pa
Admin panel |  |  |  | Admin P | Admin P | Admin P | Admin P
Instructor panel | [5 empty] | Instructo | Instructo
- Newsfeed | [5 empty] | Newsfee | Newsfee
- Course management | [6 empty] | Course M
- Student entry management
- Attendance monitoring
- Tasks distribution / posting
- Grades posting
Student panel | [5 empty] | Student P | Student P | Student P
- Newsfeed | [5 empty] | Newsfee |  | Newsfee
- Course enrollment | [6 empty] | Course e | Course e
- Personal attendance reports
- Tasks viewing / submission / reports
- Grade reports
Documentation | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Chapter 1 - Introduction
- Project Context
- Purpose and Description
- Objectives
- Scope and Limitations
Chapter 2 - Review of related…
- Review of Related Literature
Chapter 3 - Technical background
- Summary of the technical feasibility.
Chapter 4 - Methodology
- Requirements specification
- Analysis
- Design
- Development and Testing
Chapter 5 - Recommendation
- Implementation plan
LEGENDS |  | Priority of the day
Minor task / progression
Task finished